## Risk Register
Cybersecurity Risk Register- March 7, 2026
Risk ID | Asset | Threat | Asset Owner | Vulnerability | Existing Controls | Likelihood | Impact | Inherent Risk | Control Effectiveness | Residual Risk | Mitigation Strategy | Risk Owner | Remediation Date | Review
RR-001 | Active Directory | Privilege Escalation | IT Director | Weak Passwords | MFA, RBAC, GPO | 4 | 5 | 20 | 4 | 16 | Stricter Password Policies, Enforcing PAM, Quarterly Access Reviews | CISO | 2026-09-07 | Quarterly
RR-002 | Admin Accounts | Credential Theft | IT Director | Phishing | MFA, PAM | 4 | 5 | 20 | 3 | 12 | Enforce PAM, Implement Phishing-Resistant MFA | CISO | 2026-09-07 | Bi-Annually
RR-003 | Backup System | Ransomware and Cyber Attack | IT Operations Manager | Misconfiguration | Firewall Rules, Network Segmentation, Encryption at Rest and in Transit, Immutable Backups, EDR | 4 | 5 | 20 | 2 | 8 | Enforce Patch Management, Conduct Regular Backup Testing, Strengthen Network Segmentation | IT Operations Manager | 2026-09-07 | Bi-Annually
RR-004 | Backup System | Physical Destruction | IT Operations Manager | Lack of Geographic Redundancy | Geographic Redundancy, Offsite Storage, Vaults and Restricted Access, 3-2-1 Backup Policy | 2 | 5 | 10 | 2 | 4 | Enforce Geographic Redundancy, Regular Physical Security Audits, Regular Backup Testing | IT Operations Manager | 2026-12-07 | Annually
RR-005 | Company Website | DDos Attack | Web Development Manager | Insufficient Rate Limiting and DDoS Protection | Cloudflare, Rate Limiting, Firewall Rules | 3 | 3 | 9 | 2 | 4 | Upgrade DDoS Protection and Conduct Regular Load Testing | Web Development Manager | 2026-12-07 | Annually
RR-006 | Company Website | SQL Injection | Web Development Manager | No Web Application Firewall and Invalid User Inputs | Web Application Firewall, Input Validation, Parameterised Queries, Database Monitoring | 4 | 5 | 20 | 4 | 16 | Implement a Strong Web Application Firewall, Enforce Input Validation, Conduct Regular Penetration Testing | Web Development Manager | 2026-09-07 | Quarterly
RR-007 | Customer Database | Unauthorized Access | Chief Data Officer (CDO) | Compromised Credentials, Weak Access Controls, Unencrypted Data | MFA, Hashing, RBAC, Encryption at Rest | 4 | 5 | 20 | 3 | 12 | Strict RBAC, Implement Database Activity Monitoring, Quartely Access Reviews | Chief Data Officer (CDO) | 2026-09-07 | Bi-Annually
RR-008 | Employee Email | Phishing | IT Director | Lack of Security Awareness Training, No MFA, No Email Filter | Email Filter, MFA, Security Awareness Training, EDR | 5 | 4 | 20 | 3 | 12 | Enforce MFA, Advanced Email Monitoring, Conduct Regular Phishing Sim Training | IT Director | 2026-09-07 | Bi-Annually
RR-009 | Employee Laptops | Malware | IT Director | Compromised Removable Media, Weak Endpoint Protection | Anti-Malware Software, EDR, USB Port Restrictions, Full Disk Encryption, Patch Management, MDM | 4 | 4 | 16 | 2 | 6 | Restrict USB Access, Enforce EDR, Implement MDM to Monitor and Manage Employee Laptops | IT Director | 2026-12-07 | Annually
RR-010 | Firewall | Misconfiguration | IT Security Manager | Outdated Software, Weak Firewall Rules | Regular Auditing and Updates, Network Monitoring, IDS | 3 | 5 | 15 | 2 | 6 | Enforce Regular Updates, Quarterly Firewall Rule Reviews, Implement Network Monitoring | IT Security Manager | 2026-12-07 | Annually
RR-011 | HR Database | Malicious Internal Access | HR Director | Unnecessary Access Privileges, No Access Monitoring, No Data Loss Prevention, No Separation of Duties | PAM, RBAC, Access Logging, DLP | 3 | 4 | 12 | 2 | 5 | Enforce Least Privilege, Conduct Quarterly Access Reviews, Implement Audit Logging | HR Director | 2026-12-07 | Annually
RR-012 | Internal Network | Lateral Movement | IT Director | Lack of Network Segmentation, No Offboarding Process | Network Segmentation, IDS, RBAC, Offboarding Process, Network Monitoring | 4 | 5 | 20 | 2 | 8 | Implement Network Segmentation, Deploy IDS, Enforce Strict Offboarding Process | IT Director | 2026-09-07 | Bi-Annually
RR-013 | Payment System | Man-in-the-Middle Attack | Chief Financial Officer (CFO) | Unencrypted Data in Transit, Weak SSL/TLS Configuration | Firewalls, Strong SSL/TLS Encryption, PCI DSS Compliance, Tokenisation, IDS | 3 | 5 | 15 | 2 | 6 | Enforce SSL/TLS Encryption, Maintain PCI DSS Compliance, Deploy Tokenisation | Chief Financial Officer (CFO) | 2026-12-07 | Annually
RR-014 | Source Code Repository | Code Theft | Chief Technology Officer (CTO) | Hardcoded Credentials, Weak Access Controls | RBAC, MFA, Code Reviews, Audit Logging, Secret Scanning | 3 | 4 | 12 | 2 | 5 | Implement a Strong MFA, Conduct Regular and Random Code Reviews, Deploy Secret Scanning | Chief Technology Officer (CTO) | 2026-12-07 | Annually
RR-015 | Vendor Access | Third Party Data Breach | Chief Procurement Officer (CPO) | Excessive Vendor Permissions, Lack of Vendor Monitoring | Vendor Risk and Security Assessment, Least Privilege Access, Vendor Access Monitoring, Contractual Security Requirements, MFA | 4 | 5 | 20 | 3 | 12 | Enforce Least Privilege For Vendor Access, Regular Vendor Security Assessments, Vendor Activity Monitoring | Chief Procurement Officer (CPO) | 2026-09-07 | Bi-Annually
RR-016 | VPN Systems | Unpatched Vulnerabilities | Network Security Manager | Outdated Firmware, No Patch Management | Regular Patch Management, MFA, RBAC, VPN Activity Monitoring, IDS | 4 | 5 | 20 | 2 | 8 | Implement Regular Patch Management, MFA For VPN Connections, Monitor VPN Activity | Network Security Manager | 2026-09-07 | Bi-Annually

## Legend
Legend
Likelihood & Impact Scale |  | Control Effectiveness Scale |  |  | Risk Level Scale
Score | Label | Score | Label | Meaning | Score | Label | Review Frequency
1 | Very Low | 1 | Fully Effective | Fully Implemented and Monitored | 1-7 | Low | Annually
2 | Low | 2 | Mostly Effective | Mostly Effective With Minor Gaps | 8-14 | Medium | Bi-Annually
3 | Medium | 3 | Partially Effective | In Place But Inconsistent | 15-19 | High | Quarterly
4 | High | 4 | Mostly Ineffective | Significant Gaps Remain | 20-25 | Critical | Monthly
5 | Critical | 5 | Ineffective | Little To No Controls In Place

## Summary
Risk Level | Number Of Risks
Critical (20-25) | 0
High (15-19) | 2
Medium (8-14) | 7
Low (1-7) | 7
Total Risks | 16